## Sheet1
Level | ID | Activity | Responsible Party | Duration | Start Date | End Date | Status | % Completion | Dependency | RAG Status | Comments
Initiation
1 |  | Project Creation in Clarity & Bind with BP in GPDM |  |  | N/A | N/A | Completed | 100% |  | C
1 |  | Project Charter |  |  |  |  | Completed | 100% |  | C | All to review and provide comment by 17Nov
1 |  | BIA |  |  |  |  | Completed | 100% |  | C
1 |  | Lean Thinking Toolkit |  |  |  |  | Completed | 100% |  | C
Definition
1 |  | Business Requirement |  |  |  |  | Completed | 100% |  | C | Nicole / Qu Gang to signoff by 05Nov.
1 |  | Architecture Review
2 |  | AR Approval |  |  |  |  | Completed | 100% |  | C
2 |  | EIM Submission |  |  |  |  | Completed | 100% |  | C | EIM number: 3489794 Approved with condition Original EIM: 1169149
2 |  | SDD (Solution Design Doc) |  |  |  |  | Completed | 100% |  | C
2 |  | SAB Approval |  |  |  |  | Completed | 100% |  | C | - SAB Approval process: submit before each Tues, then can be approved in the next Mon. - SAB approva was obtained on 04Oct.
1 |  | ITSA
2 |  | ITSA Engagement |  |  |  |  | Completed | 100% |  | C | ITSA CNAPS: 8869 https://saa.hk.hsbc:30000/itsa/project/assessnfr.htm?pid=8869
2 |  | G1.01 - Operational Level Agreement (OLA) | HBCN Quality Team Deric Chen Jan Chen |  |  |  | Completed |  |  | C | For the service availability change, you can send the updated OLA template to us once confirmed. While for the CBS tier change, you may send the request to global D&P team for review (CBS submission). Once it’s accepted, global D&P will inform our regional team for OLA record update in PLADA. When combing HVPS+HVPS, define a reasonable maintenance window (during which the system release is allowed).
3 |  | Technology service information that conforms to global OLA guidelines and standards, needs to be documented, reviewed, approved, and uploaded into the Group repository (PLADA). | Jane Chen |  |  |  | Completed |  |  | C
3 |  | CBS (Critical Business Service) Approval |  |  |  |  | Completed |  |  | C | Ray K L TANG <raytang@hsbc.com.hk>; Susan POWELL <susan.powell@noexternalmail.hsbc.com>; Vinay KASHYAP <vinay.kashyap@hsbc.co.in> to advise the progress. Because Tier 1 can't fulfill 0.5 hr recovery time. Can only categorize as Tier 0. Alex Wu advised Tier 0/Tier1 has to go through CBS review (critical business service process) -- with proposed solution. CBS sharedpoint: http://teams.global.hsbc/hts/CBSInvReqMgt/SitePages/Home.aspx Submitted.
2 |  | G1.02 - Performance and Efficiency | Project Team GPCoE -Asia Eric CY Lee |  |  |  | Completed |  |  | C | - Elaine is helping on the questions in Decision tree (Request #8869: http://teams.global.hsbc/hts/GPCoE/Lists/Decision%20Tool/AllItems.aspx?View={3A33CD71-6017-489D-80FE-E94EEAC5152E}&FilterField1=LinkTitle&FilterValue1=HBCN%20Payment%20System%20Infrastructure%20Improvement) to see whether GPCoE shall be involved. Submit Form to engage GPCoE Team on Performance Test. (A form has been prepared and saved, pending for submission) - Need to involve Testing Team? Any cost? - Consider to leverage vendor simulator We've installed JMeter, tested by project team ourselves. After project team complete the performance test, can mark this item as completed.
2 |  | G2.02 - Service Continuity | Service Resilience & Hosting -HK |  |  |  | Completed |  |  | C | - After failover test completion, signoff is required.
3 |  | BIA & PDR |  |  |  |  | Completed |  |  | C | Linda has shared the approved BIA to beloow contacts, if no comment recieved by 17Jan, to close this item. Jake J PENG <jake.j.peng@hsbc.com.hk>; Kerry S W YAU <kerryswyau@hsbc.com.hk>; Service Resilience And Hosting ASP <serviceresilienceandhostingasp@hsbc.com.hk>; Victor C W WAN <victor.c.w.wan@noexternalmail.hsbc.com>
3 |  | ITSRP (IT Service Recovery Plan) |  |  |  |  | Completed |  |  | C | Need to work with ITID to define the ITSRP Update ITSRP (of CNAPS), submit to the contact of this item by early May. (3 weeks before the drill)
3 |  | Disaster Recovery/Roleswap Exercise |  |  |  |  | Completed |  |  | C
2 |  | 3.01 - Architectural Compliance | Project Team Alex Wu |  |  |  | Completed | 100% |  | C | SAB for CNAPS has been approved. This item can be closed.
2 |  | G3.03 - Service Placement | Project Team Alex Wu |  |  |  | Completed | 100% |  | C | SPB (Service Placement Process) -- alex Wu confirmed it's part of SAB, and can be marked as completed with SAB approval is in place.
2 |  | 3.05 - HTS Security Compliance (GASRA) | Project Team Information Security Risk (ISR) IT Security China |  |  |  | Completed |  |  | C | Comet request has been submitted to engage ISR: Request ID: 20335 (Comet ID: 42965) - Confirmed application security test is not required. - Infra penatration test is required, a GZ teammate Lynn Y Y CHENG has been assigned to perform infra panetration test in apr. - New server compliance check. GSR -13381560
3 |  | New Server Compliance Check (Lead time: 1 week since GSR is approved till compliance check completed) | Terry Wu |  |  |  | Completed |  |  | C
3 |  | Priviledged account needs to be uploaded to PPM and hand over to IT Security Liu chen chu has provided guide. Lead time 1 week since GSR is approved till request is completed. |  |  |  |  | Completed |  |  | C
3 |  | ToE Form |  |  |  |  | Completed |  |  | C | Have written to ISR contacts to ask for TOE form. Also asked for a contact to work with for the rest of the ITSA items about ISR. (Tc raised to Archana GEETEY <archana.geetey@noexternalmail.hsbc.com>) Jenny to help.
2 |  | G4.02 - Operations Acceptance Testing (OAT) | Project Team |  |  |  | Completed |  |  | C | OAT shall be performed by Project Team. There's no specific requirement from Eric Lee. Can mark as completion by ourselves after OAT. All the testing activities have been completed.
2 |  | G5.01 - Operational Requirements | DCSM - Service Implementation & Support Management -HK |  |  |  | Completed |  |  | C | Linda Fan to coordinate. - ITID need to share the relevant documents to HK DCSM for record purpose. - Linda Fan shall also check with Alphonse S C LING / Victor C W WAN (HK DCSM) to understand whether their teams also need to be involved for any testing / checking? [Confirmed no need to test] In Filenet: need to update ID #2351 and #7380 to update the existing documentation for CNAPS To work with Linda Fan for the documents required.
3 |  | Actions in the previous mail (2016/11/16 (周三) 14:48) - 2 mandatory documents to be prepared each new GSD Asset ID (to work with Linda fan). Refer to the 2 existing files on Filenet. After update, send to Victor to upload to FileNet. Victor shared: if no procedure for HK Datacentre operations, then no need to perform command simulation test. in this case, after review the document, NFR G5.01 could be GREEN |  |  |  |  | Completed |  |  | C | Can't open those links. Below contact to advise: Victor C W WAN <victor.c.w.wan@noexternalmail.hsbc.com>; Grace B Y CAO <gracebycao@hsbc.com.cn>; Cobe Q M HUANG <cobeqmhuang@hsbc.com.cn>
3 |  | All operational documentation and procedures should be well-defined, documented and tested before production launch. |  |  |  |  | Completed |  |  | C
2 |  | 5.03 - External Suppliers - 3rd Party Support | Project Team |  |  |  | Completed | 100% |  | C | Project Team to check whether the requirement mentioned in this item can be fulfilled. If yes, mark completion for this item on ITSA sharedpoint.
2 |  | G5.06 - Configuration Management | Configuration Management (Global) |  |  |  | Completed |  |  | C | CICF attached into sharedpoint. SME to advise whether fine to close this item.
2 |  | G5.08 - Global Capacity Management | ITID Capacity Management |  |  |  | Completed |  |  | C | Jenny help to raise an assessment reuqest. The capacity management team will review, and then wait till performance test finish to provide the result to them. 1. Process refer to: https://team.global.hsbc/sites/ITACM/ITCM/Welcome/SitePages/HOST ITID Capacity Management.aspx 2. Contact: Cerys Y WU <cerys.y.wu@hsbc.com.hk>
2 |  | G5.09 - Service Monitoring & Alerting | Enterprise System Management -HK David Y P CHENG/HTSA/HSBC |  |  |  | Completed |  |  | C | Contact: David Y P Cheng - Engagement email sent to PM. by NFR5.09 Automation (FROM Dcsm SSE SERVICE MONITORING, 2016/11/22 07:33) - Raise GSR to add xmatter / alert (Terry is doing) Terryhas shared below info to David_Y_P_CHENG to check whether it meet requirements. 1. The completed GSR number (Terry asked the other teammates help) 2. signoffed server list GSR number: GSR-13149521 GSR-13165025 GSR-13226717 Server List: CNAPS ORACLE PROD Server1 (cn000zhj1193) CNAPS ORACLE PROD Server2 (cn000zhj1194) CNAPS WAS PROD Server1 (cn000zhj1195) CNAPS WAS PROD Server2 (cn000zhj1196) CNAPS MQ PROD Server1 (cn000zhj1197) CNAPS MQ PROD Server2 (cn000zhj1198) CNAPS App PROD Server1 (cn000zhj1199) CNAPS App PROD Server2 (cn000zhj1200) CNAPS ORACLE DR Server1 (cn000ifc1125) CNAPS ORACLE DR Server2 (cn000ifc1126) CNAPS Was DR Server1 (cn000ifc1127) CNAPS Was DR Server2 (cn000ifc1128) CNAPS MQ DR Server1 (cn000ifc1129) Green light has been granted. CNAPS MQ DR Server2 (cn000ifc1130) CNAPS App DR Server1 (cn000ifc1131) CNAPS App DR Server2 (cn000ifc1132)
2 |  | 6.02 - Release Management | Application Lifecycle Management (Open) -HK |  |  |  | Completed |  |  | C | Eric shared G3 is a mandatory requirement for application deployment. If together with project launch, G3 can't be implemented, this governance team would ask for a committed date by when G3 can be used, and grant us a grace period. They will then provide a Amber status for this item under ITSA, and will lead to a conditional ITSA signoff (not affecting the project launch) To study with ITID whether any technical issue to deploy G3. Andrew once shared some info about G3 as well. Then: Please answer the questions below and send to ALM team SMEs for necessary actions and sign-off: Chris Q J HU 1. Application name? 2. What is the Source Control tool (eg RTC)? 3. Application platform (eg Linux , Windows)? 4. Release type (eg WAS, DB etc)? 5. What is the release tool? 6. Any deployment would be run or triggered manually in Prod environment? 7. If answer to 6. is yes, please tell the name and role (eg ITID / SwD) of the team that will run or trigger it in Prod. (why manual deployment is used?) 8. If G3 is used for the release, please provide the G3 project area name. (G3 may not be implemented in day 1, can agree a target implementation date and seek for condictional signoff)
2 |  | ITSA Completion Cert |  |  |  |  | Completed |  |  | C
1 |  | Vendor
2 |  | Finalize Change Scope & Quotation from vendor |  |  |  |  | Completed | 100% |  | C | Vendor change scope shall ensure application coding can work with the new Infra architecture (esp MQ ) and DB connectivity after Oracle switch over (some code changes may be required to ensure application do not need to re-bounce after DB switch over). Actually, the same applies to HUB code as well.
3 |  | CNAPS - 评审《业务需求说明书》 | Y-Link |  |  |  | Completed | 100% |  | C
3 |  | CNAPS - 《需求分析说明书》 | Y-Link |  |  |  | Completed | 100% |  | C
2 |  | SoW approval by GCIO |  |  |  |  | Completed | 100% |  | C | GCIO approval is in place already.
2 |  | Contract signoff with Y-Link | GPU/Y-Link/SwD |  |  |  | Completed | 100% |  | C | - PO via BuySmart in progress, pending for GPU Collin Tam's approval. (with regional support on tender waiver) - Y-Link has provided drafted SoW. To review and comment. - Ensure all the Recovery / Monitoring scenario are covered in subsequent testing ( by Vendor & ITID ) and written into the SoW
1 |  | Find out Regulatory Joint-Test / Inspection process |  |  |  |  | Completed |  |  | C | PBOC advised there's no joint-test requirement, as their DR project has not been established yet. No specific inspection requirement, before project launch, draft a regulatory report with bank's chop and submit to PBOC will be fine.
1 |  | Regulatory Communication / report with bank's chop |  |  |  |  | Completed |  |  | C | To be planned after confirmating with PBOC about their joint-test/inspection process "2017年6月30日完成备份系统建设，并将完成情况以正式文件报告中国人民银行上海分行"
1 |  | Priviledged Account Creation | ES |  |  |  | Completed |  |  | C
1 |  | Failover procedure & optimization design |  |  |  |  | Completed |  |  | C
1 |  | Functional Spec - For application changes | [8 empty] | 1. Vendor system (possible changes): - Application changes for migration from SUSE to RedHat OS platform during the evergreen. (Vendor has confirmed the coding can be independent with OS upgrade) Application changes are also required to cater for infrastructure changes. 2. HUB - shall also review whether changes are required to cater for the MQ infrastructure.
2 |  | CNAPS - 《系统设计说明书》 | Y-Link |  |  |  | Completed | 100% |  | C | Vendor provided the draft version on 24Nov. Andrew / Linda / Elaine to review and comment. Need to discuss any application level change is needed to achieve 30 mins recovery.
2 |  | HUB - Functional Spec | GLTc HUB Team |  |  |  | N/A | 100% |  | C | e.g. any change required on HUB to support MQ . HUB team advised there shall be no change on application level required.
1 |  | Technical Spec - For application changes
2 |  | CNAPS - Technical Spec | Y-Link |  |  |  | Completed | 100% |  | C | To ask XiaoJi to provide in due course.
2 |  | HUB - Technical Spec | GLTc HUB Team |  |  |  | N/A | 100% |  | C
Execution
| 1.1 | NH (DR) | TS/ES |  | 2017-08-14 | 2017-08-18 | Not Started
| 1.1.1 | Cabling Requirement | PCCW |  |  |  | Not Started
| 1.2 | Cabling Work | Vendor |  |  |  | Not Started
| 1.2.1 | CNAPS Server Delivery | Vendor |  |  |  | Not Started
| 1.3 | CNAPS Server Delivery | ESS -Terry |  |  |  | Not Started
|  | CO for loading to the rack | NES - Alan |  |  |  | Not Started
| 1.4 | CO for network configuration | TS |  |  |  | Not Started
| 1.4.1 | DRN Network Equipment Installation | TS |  |  |  | Not Started
| 1.5 | DMZ Network Equipment Installation |  |  |  |  | Not Started
| 1.5.1 | SAN Switch arrange zone |  |  |  |  | Not Started
| 1.6 | SAN Switch cabling |  |  |  |  | Not Started
| 1.6.1 | FQDN | application |  |  |  | Not Started
| 1.6.2 | FQDN request submission | HK -TS |  |  |  | Not Started
| 1.7 | FQDN enable |  |  |  |  | Not Started
| 1.7.1 | F5 | application |  |  |  | Not Started
| 1.7.2 | F5 script creation request | China TS- Tony |  |  |  | Not Started
| 1.7.3 | Script creation | application |  |  |  | Not Started
| 1.7.4 | Script GSR submission CO | HK - TS |  |  |  | Not Started
| 1.8 | F5 script deployment |  |  |  |  | Not Started
| 1.8.1 | Firewall | application |  |  |  | Not Started
| 1.8.2 | Firewall rule request submission | China TS- Peng |  |  |  | Not Started
| 1.9 | Firewall rule enable |  |  |  |  | Not Started
| 1.9.1 | CNAPS Server Provision | ES-Terry/Wen hao |  |  |  | Not Started
| 1.9.2 | CNAPS application (DMZ) | ES-Terry/Wen hao |  |  |  | Not Started
| 1.9.3 | MQ Server | ES-Terry/Wen hao |  |  |  | Not Started
| 1.9.4 | Oracle Server | ES-Terry/Wen hao |  |  |  | Not Started
| 1.9.5 | Was server | ES-Terry/Wen hao |  |  |  | Not Started
| 1.9.6 | signature server installation and configuration |  |  |  |  | Not Started
|  | Handover to Local ADM team | ES |  |  |  | Not Started
| 1.11.1 | Leaseline | ITID PM |  |  |  | Not Started |  |  |  | IBS->New extranet platform->old extranet platform->old leased line. N/A
| 1.11.2 | Leaseline application to CCPC and PBOC | regulatory |  |  |  | Not Started |  |  |  | IBS->New extranet platform->old extranet platform->old leased line. N/A
| 1.11.3 | new leaseline setup permission | PM |  |  |  | Not Started |  |  |  | IBS->New extranet platform->old extranet platform->old leased line. N/A
| 1.11.4 | BU cost approval | TS |  |  |  | Not Started
| 1.11.5 | Place order | CU? |  |  |  | Not Started
| 1.11.6 | Lease line deliver | TS |  |  |  | Not Started
|  | Leaseline Cutover *** Beware & Ensure all server boxes are not connected to Production Network before formal release date ( end June ) during ALL testing phases. To include the network detailed switch plan into the cutover plan. | TS |  |  |  | Not Started
| 1.11.7 | Lease line configuration | ALL |  |  |  | Not Started
| 1.11.8 | Onsite Inspection | ALL |  |  |  | Not Started |  |  |  | No onsite inspection is required from PBOC
1 |  | Development - Application | [8 empty] | No code change
1 |  | Unit Test | [8 empty] | Unit test is not required, since there's no code change on HUB.
1 |  | Test Strategy |  |  | 2017-08-14 | 2017-08-18 | Not Started |  |  | C
1 |  | Auto Monitoring & Alerting on PROD/DR | ITID / Y-link |  |  |  | Not Started |  |  | C
1 |  | SIT
2 |  | Confirm the environment to be used for SIT |  |  |  |  | Not Started |  |  |  | It's confirmed the SIT shall be executed in DR/PROD after evergreening.
2 |  | SIT Test Case Preparation |  |  | 2017-08-14 | 2017-08-18 | Not Started |  |  | C
2 |  | SIT Testing Environment Readiness |  |  | 2017-08-14 | 2017-08-18 | Not Started |  |  | C
3 |  | CNAPS Architecture Readiness | ITID |  | 2017-08-14 | 2017-08-18 | Not Started |  |  | C | Leased line between new network platform and PBOC to be ready by end Apr.
4 |  | DR machine |  |  |  |  | Not Started |  |  | C
4 |  | PROD machine |  |  |  |  | Not Started |  |  | C
4 |  | MQ (PROD+DR) |  |  |  |  | Not Started |  | Terry will try to complete by 03Mar. In the worst case, the MQ setup will be completed by 10Mar | C
4 |  | HUB testing env -MQ interface | GLTc HUB Team |  | 2017-08-14 | 2017-08-18 | Not Started |  |  | C
4 |  | F5 | SwD / ITID |  |  |  | Not Started |  | CO | C
4 |  | FQDN + GSS | SwD / ITID |  |  |  | Not Started |  | GSR | C
4 |  | Firewall Rule | SwD / ITID |  |  |  | Not Started |  | Request Form | C
4 |  | FQDN for Oracle | SwD / ITID |  |  |  | Not Started |  | GSR | C
4 |  | Email Staging Server | SwD |  |  |  | Not Started |  |  | C
5 |  | Firewall request (if needed) | SwD |  |  |  | Not Started |  |  | C
5 |  | apply for new mailbox | SwD |  |  |  | Not Started |  |  | C
5 |  | Submit GSR to apply for access to mail staging server | SwD |  |  |  | Not Started |  |  | C
4 |  | CNAPS DR application deployment |  |  |  |  | Not Started
4 |  | CNAPS PROD application deployment |  |  |  |  | Not Started |  | Pending for Terry to complete OS installation for PROD | C | CNAPS PROD Appliaction deployment has not be completed.
3 |  | HUB SIT env Readiness | GLTc |  |  |  | Not Started |  |  | C
3 |  | HUB-CNAPS MQ setup/config | GLTc / Y-Link |  |  |  | Not Started |  |  | C
3 |  | End-to-End conectivity test for SIT Env | ITID / Y-Link / GLTc |  |  |  | Not Started |  |  | C
2 |  | PDUTE (Production Data usage in Test Env) approval |  |  |  |  | Not Started |  |  | C | http://perfectforms.hk.hsbc/perfectformsSSO/player.aspx?f=8HgAAg2E Request ID: 3985
2 |  | SIT Data Preparation |  |  | 2017-08-14 | 2017-08-18 | Not Started |  |  | C | - Before Data conversion test, y-link to prepare SIT data themselves. - After 1st round of data conversion test, the SIT data can use the masked production data.
2 |  | SIT Execution |  |  | 2017-08-21 | 2017-09-15 | Not Started |  |  | C
2 |  | Performance Test -- send the performance statistics to Matthew K H LEUNG for a double check, and they could provide some tuning solution if any performance impact is found |  |  | 2017-09-04 | 2017-09-15 | Not Started |  |  | C
1 |  | Analysis on impact on users, and plan communication (e.g. Icon change, etc.) - PB Client - WAS Client (SD PSV, HUB PSV, SD BKO as contingency for account upload) | 对user的影响 URL, CONFIG FILE etc. |  | 2017-09-04 | 2017-09-15 | Not Started |  |  | C | Confirmed with vendor: - For WAS Client, a new URL will be provided. - For PB Client, the config file needs to replaced by a new one on User's PC.
1 |  | Cutover Plan & FallBack Plan & Contingency Plan |  |  | 2017-08-21 | 2017-09-15 | Not Started |  |  | C
Not Started
1 |  | Actions to address MAP (CNAPS RTO > 4 hours) - To provide agreed evidence to George |  |  |  |  | Not Started |  |  | C
1 |  | UAT (If needed, in parallel with SIT)
2 |  | Confirm the environment to be used for UAT |  |  |  |  | Not Started |  |  | C | It's confirmed after evergreening DR/PROD will be used for UAT (the same with SIT)
2 |  | Coummnication to users for UAT rrangement |  |  | 2017-08-21 | 2017-08-25 | Not Started |  |  | C
2 |  | UAT Test Case Preparation |  |  | 2017-08-21 | 2017-08-25 | Not Started |  |  | C
2 |  | UAT Testing Environment Readiness |  |  |  |  | Not Started |  |  | C | Use the same environment with SIT.
2 |  | UAT Execution |  |  | 2017-08-28 | 2017-09-15 | Not Started |  |  | C
2 |  | Confirm RTO/RPO with business and seek for signfof. | GLCM/OPS/IT |  | 2017-09-15 | 2017-09-15 | Not Started |  |  | C | Notification sent to business. No concern received.
1 |  | OAT
2 |  | OAT Test Case Prparation | ITID |  |  |  | Not Started |  |  | C | Combined in SIT/UAT test case
2 |  | OAT Execution | ITID |  |  | 2017-09-15 | Not Started |  |  | C | Together with SIT/UAT
1 |  | User Communication about the project launch: GLCM/SD PSV/HUB OPS… (e.g. any icon change/access info change, etc) |  |  | 2017-08-28 | 2017-09-15 | Not Started |  |  | C
1 |  | Security Test (if needed) |  |  |  |  | Not Started
2 |  | Application Penetration Test |  |  |  |  | N/A |  |  |  | As reviewed by IT Security: Tc T C HE, there should be no application penetration test required, since there's no functional change.
2 |  | Infra Security Test / Infra Vulnerability Scan | Lynn Y Y CHENG |  | 2017-08-28 | 2017-09-15 | Completed |  | COMET URL | C | '- Please ensure all required apps/system/services are completely installed, configured, and deemed as final prior to security testing. If there would be any material or configuration changes (ie, new open ports – services/protocol, new certificate, new ciphers) upon security testing, then it would invalidated or nullify the current security assessment. Completed, 6 low risk items. Terry / Jian to advise follow-up actions and target date.
1 |  | Test Phase Completeness Certificate |  |  | 2017-09-14 | 2017-09-15 | Not Started |  |  | C
1 |  | IT Procedure Update / Approval (if needed) All to advise the procedure which needs to be updated. |  |  | 2017-09-18 | 2017-09-22 | Not Started |  |  | C | e.g. HUB role-swap procedure: When HUB failover to HUB DR, HUB should reconnect MQ. This should be supplemented to HUB Role-swap procedure. ESS and Network have confirmed no other documents need to be updated, in addition to those documents mandated by ITSA.
2 |  | Failover Procedure (ITSRP) | All |  | 2017-09-18 | 2017-09-22 | Not Started |  | add back NH Center | C | Draft under review by SME / Audit Uploaded to filenet, with doc ID 0000041270
3 |  | CNAPS Application Procedure / 用户手册 | Y-Link Huateng, 是否需要调整 |  | 2017-09-18 | 2017-09-22 | Not Started |  |  | N/A | e.g. <CNAPS故障恢复手册v1.0> needs to be updated
1 |  | On-Site Inspection By PBOC (if needed) |  |  |  |  | Not Started
2 |  | Prepare the materials for on-site inspection & Self-check the readiness | All |  | 2017-09-11 | 2017-09-15 | Not Started
2 |  | Request PBOC to perform on-site inspection | All |  | 2017-09-18 | 2017-09-22 | Not Started
2 |  | PBOC to perform on-site insepction | All |  | 2017-09-18 | 2017-09-22 | Not Started
1 |  | Regulatory filing for service outage (if any) during production cutover | All |  | 2017-09-18 | 2017-09-22 | Not Started |  |  | C | If the downtime of critical system is more than 3 hours. Need to submit filing report to CBRC (no matter it’s within regular maintenance window or not), and the report shall be received by CBRC 10 working days ahead.
1 |  | Pre-Launch Setup |  |  | 2017-09-18 | 2017-09-29
2 |  | Email Staging Server Production Setup | SwD |  |  |  | Not Started |  |  | C
3 |  | Firewall request (if needed. E.g. APP to PBOC Production on new extranet platform). Connectivity Test with PBOC (how?) | SwD |  |  |  | Not Started |  |  | C | Li peng confirmed the firewall request for new extranet platform is completed
3 |  | apply for new mailbox | SwD |  |  |  | Not Started |  |  | C
3 |  | Submit GSR to apply for access to mail staging server | SwD |  |  |  | Not Started |  |  | C
3 |  | Connectivity Test (e.g. sample mail) | SwD |  |  |  | Not Started |  |  | C
2 |  | Build connection between HUB Prod <-> MQ | GLTc HUB Team |  |  |  | Not Started |  |  | C
3 |  | MQ Request | GLTc HUB Team |  |  |  | Not Started |  |  | C | 2 weeks' lead time
3 |  | Update MQ related config (Naming T->P; MQ naming change (now TLHKCL02)..QM) | Y-link GLTc HUB Team ES |  |  |  | Not Started |  |  | C
3 |  | Submit GSR for DB user ID password reset and input via encryption tool: | SwD |  |  |  | Not Started |  |  | C
3 |  | Connectivity Test: HUB Pord <->MQ | GLTc HUB Team ITID |  |  |  | Not Started |  |  | C
2 |  | Re-install certificate on signature servers & Verification by Y-Link | CFCA Y-Link |  |  |  | Not Started |  |  | C
2 |  | Connectivity Test for the links which are not covered in SIT/UAT (if any) | All |  |  |  | Not Started |  |  | C
2 |  | Remove firewall rule which is only for testing purpose (if any) | SwD/Network |  |  |  | Not Started |  |  | C
Change, Transition, and Closure
1 |  | Implementation Authorization |  |  | 2017-09-18 | 2017-09-19 | Not Started |  |  | C
1 |  | Implementation Preparation |  |  | 2017-09-18 | 2017-09-29 | Not Started |  |  | C
1 |  | Technical Launch / Cutover |  |  | 2017-09-30 | 2017-09-30 | Not Started |  |  | C | CNAPS: PBOC's requirement is to launch by end of Jun2017
1 |  | Business Verification |  |  | 2017-10-02 | 2017-10-02 | Not Started |  |  | C
1 |  | Post Implementation Support |  |  | 2017-10-02 | 2017-10-30 | Not Started |  |  | C
1 |  | Project Completion Certificate |  |  | 2017-10-31 | 2017-10-31 | Not Started |  |  | C
Deploy RTC for source control in 3 months (by Aug) Deploy G3 for code deployment (by Aug). Seek for guidance from Terence.
Deploy Control-M
8 low risk items identified during infra pene test.Need to close in 6 months.
HUB OPS Request: - Onboard GIAM - Application submission via GSR - enablement
Long term solution for risk mitigation: APP数据库帐号改成新帐号(do not use CNAPSAPPP anymore)
SSL Cert of MQ Gateway will be expired in 2 years. Next check point: early 2019.